Tuolumne River Restoration Monitoring

| ## Task | Task Title | Deliverable | Estimated Completion Dates |
| --- | --- | --- | --- |
| 1 | Project Mgmt & Adm | - Semi-Annual Progress Report | Due: - Jan. 10, 2007 - Jul. 10, 2007 - Jan. 10, 2008 - Jul. 10, 2008 - Jan. 10, 2009 |
|  |  | - Monthly Invoice | Due by XX of each month from August 2006 through August 2009. |
|  |  | - Subcontract documentation | To be provided within 30 days of subcontract execution. |
| 2 | Public Participation | - Pre and post meeting materials - Public Notices - Public Meetings - Meeting Summaries | - Within 6 months of contract execution - 30 days prior to each scheduled public meeting - 12th and 24th month months after contract execution - 10 working days after each public meeting |
| 2.1 | Coordinate with TRTAC, TRTAC Monitoring Subcommitee, and Lower Tuolumne River Coalition | - Meeting summaries and minutes of the TRTAC, TRTAC Monitoring Subcommittee, and Tuolumne River Coalition meetings. | - To be included as attachment to semi annual progress reports (see Task 1). |
| 2.2 | Produce and Distribute Interpretive Brochures for the Restoration Projects and Monitoring | - One hard copy and one electronic copy of an interpretive brochure for each restoration project and related monitoring. | - To be submitted June 30, 2009 |
| 2.3 | Present findings at CALFED Science Conference and Prepare Manuscript(s) for Publication | - Presentation(s) at at least one CBDA Science Conference; up to three manuscripts submitted to peer-reviewed journals. | - At least one presentation at 200XX CALFED Science Conference - Manuscripts to be submitted by June 30, 2009 |
| 3 | Environmental Compliance and Permitting | - Not applicable | - Not applicable |
| 4 | 7/11, M.J. Ruddy, and SRP 9 Monitoring |  | - To be included in draft and final report (see Task 8) |
| 5 | Fine Sediment Management Monitoring |  | - To be included in draft and final report (see Task 8) |
| 6 | Monitoring of Cumulative Effects on Target Populations [Chinook salmon and O. mykiss] |  | - Relevant sections of annual report to FERC to be submitted by May 1 2007 through 2009. - To be included in draft and final report (see Task 8) |
| 7 | Aerial Photography and Bathymetry |  | - To be included in draft and final report (see Task 8) |
| 8 | Draft and Final Report | - Draft Report - Final Report | - To be submitted April 24, 2009 - To be submitted June 30, 2009 |
| 9 | Project Close Out | - Project Close Out Report - Final Invoice | - 30 days prior to end of the contract term (June 1, 2009) - 30 to 60 days after Final Report is approved |