## Sheet1
Tuolumne River Restoration Project Monitoring
(DRAFT - October 28, 2006)
* This table includes projects implemented by TID/TRTAC, FOT, TRPT, and CDFG and present completed and planned future project-related monitoring activities. River-wide monitoring of Chinook salmon and O. mykiss are provided in a separate table. Additional detail on monitoring report status for TID/TRTAC projects and funds included in the CALFED PSP are also provided in a separate table.
** Note that all available project monitoring funds for TID/TRTAC projects have been expended. The approved 2006-08 CALFED grant will fund future monitoring at these sites.
Project | Project | [10 empty] | CALFED PSP
Proponent | Monitoring Activity | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008
TID/TRTAC | SRP 9 (constructed 2001)
Digital terrain mapping | bar: 1996; 2002
Cross section surveys and long profile | bar: 1998 to 1999; 2002; CALFED PSP 2006 to CALFED PSP 2008
Aerial photography | bar: 1998; 2002; 2005
Map channel migration and other planform changes | bar: CALFED PSP 2006 to CALFED PSP 2008
Water surface elevation during high flows | bar: 2003; 2005
Continuous water surface monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Continuous ground water monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Pebble Counts | bar: CALFED PSP 2006 to CALFED PSP 2008
Tracer Rocks | bar: CALFED PSP 2006 to CALFED PSP 2008
Habitat mapping | bar: 1998 to 1999
Habitat Modeling | bar: 2004
Electrofishing at project and control sites | bar: 1998 to 1999; 2003; CALFED PSP 2006 to CALFED PSP 2008
Mark-recapture at rotary screw traps | bar: 1998 to 1999
| Focused predation study | CALFED PSP 2006: X 2
Seine surveys (winter/spring) | bar: CALFED PSP 2006 to CALFED PSP 2008
As-built vegetation maps/post-irrigation survival | bar: 2002
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based riparian recruitment monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Avian monitoring (combined with vegetation relevée) | bar: CALFED PSP 2006 to CALFED PSP 2008
TID/TRTAC | SRP 10 (not yet constructed)
Digital terrain mapping | bar: 1996
Cross section surveys and long profile | bar: 1998 to 1999; CALFED PSP 2006 to CALFED PSP 2008
Aerial photography | bar: 1998; 2005 to CALFED PSP 2008
Map channel migration and other planform changes | bar: CALFED PSP 2006 to CALFED PSP 2008
Water surface elevation during high flows | bar: 2005
Continuous water surface monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Continuous ground water monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Tracer Rocks and Pebble Counts
Habitat mapping | bar: 1998 to 1999; CALFED PSP 2006 to CALFED PSP 2008
Habitat Modeling | bar: 2005
Electrofishing at project and control sites | bar: 1998 to 1999; 2003; CALFED PSP 2006 to CALFED PSP 2008
Mark-recapture at rotary screw traps | bar: 1998 to 1999
Seine surveys (winter/spring) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Avian monitoring (combined with vegetation relevée) | bar: CALFED PSP 2006 to CALFED PSP 2008
TID/TRTAC | 7/11 Phase Gravel Mining Reach (constructed 2002-03)
Digital terrain mapping | bar: 1999
Cross section surveys and long profile | bar: 1998 to 1999; 2002; CALFED PSP 2006 to CALFED PSP 2008
Channel bathymetry survey | bar: 2005
Aerial photography | bar: 1998; 2002; 2005
Map channel migration and other planform changes | bar: CALFED PSP 2006 to CALFED PSP 2008
Water surface elevation during high flows | bar: 2003; 2005
Continuous water surface monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Continuous ground water monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Pebble Counts | bar: 1998 to 1999; 2002; CALFED PSP 2006 to CALFED PSP 2008
Tracer Rocks | bar: 2005 to CALFED PSP 2008
Habitat mapping | bar: 1998 to 1999; 2002
Seine surveys (winter/spring) | bar: CALFED PSP 2006 to CALFED PSP 2008
Redd Mapping | bar: CALFED PSP 2006 to CALFED PSP 2008
As-built vegetation maps/post-irrigation survival | bar: 2003
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based riparian recruitment monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Photomonitoring of bioengineered bank protection
Avian monitoring (combined with vegetation relevée) | bar: CALFED PSP 2006 to CALFED PSP 2008
TID/TRTAC | Ruddy Phase Gravel Mining Reach (construction planned 2006)
Digital terrain mapping | bar: 1999
Cross section surveys and long profile | bar: 1999; CALFED PSP 2006 to CALFED PSP 2008
Channel bathymetry survey | bar: 2005
Aerial photography | bar: 1998; 2005
Map channel migration and other planform changes | bar: CALFED PSP 2006 to CALFED PSP 2008
Water surface elevation during high flows
Continuous water surface monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Continuous ground water monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Pebble Counts | bar: CALFED PSP 2006 to CALFED PSP 2008
Tracer Rocks | bar: CALFED PSP 2006 to CALFED PSP 2008
Habitat mapping | bar: 1998 to 1999; CALFED PSP 2006 to CALFED PSP 2008
Seine surveys (winter/spring) | bar: CALFED PSP 2006 to CALFED PSP 2008
Redd Mapping | bar: CALFED PSP 2006 to CALFED PSP 2008
As-built vegetation maps/post-irrigation survival | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based riparian recruitment monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Photomonitoring of bioengineered bank protection
Avian monitoring (combined with vegetation relevée) | bar: CALFED PSP 2006 to CALFED PSP 2008
FOT, | Bobcat Flat (FOT) (constructed 2005)
TID/TRTAC | Digital terrain mapping | bar: 2003; 2005
Cross section surveys and long profile | bar: 2003; 2005
Channel bathymetry survey | bar: 2003; 2005
Aerial photography | bar: 2005
| Water surface elevation during high flows | CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Pebble Counts | 2001: X; 2005: X; CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Tracer Rocks | 2005: X; CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Bulk samples | 2005: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Habitat mapping | 2001: X; 2005: X; CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Seine surveys (winter/spring) | CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
| Chinook salmon redd mapping | 2004: X; 2005: X; CALFED PSP 2006: X; CALFED PSP 2007: 5; CALFED PSP 2008: 5
As-built vegetation maps/post-irrigation survival | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based riparian recruitment monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Avian monitoring (combined with vegetation relevée) | bar: CALFED PSP 2006 to CALFED PSP 2008
FOT | Grayson Floodplain Restoration (FOT)
Vegetation survival | bar: 2003 to 2005
Mammal surveys | bar: 2003 to 2005
Avian monitoring (combined with vegetation relevée) | bar: 2003 to CALFED PSP 2008
FOT | Waterford Riparian Restoration Site
Plot-based vegetation monitoring (survival, % cover, and growth) | bar: CALFED PSP 2006 to CALFED PSP 2008
Plot-based riparian recruitment monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Continuous ground water monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
TRPT | Big Bend
??????? | bar: CALFED PSP 2006 to CALFED PSP 2008
TID/TRTAC, | Gasburg Creek (part of Fine Sediment Management) (construction planned for 2006)
CDFG | Gasburg Creek Sediment Source Assessment | bar: 2004
Quantify annual sediment accumulation | bar: CALFED PSP 2007 to CALFED PSP 2008
Monitor channel stability and riparian vegetation | bar: CALFED PSP 2007 to CALFED PSP 2008
TID/TRTAC | Other Fine Sediment Management
Survival-to-Emergence Study | bar: 2002
Riffle cleaning pilot study
Pool cleaning literature review | bar: 2002
Tributary sediment reconnaissance study | bar: 2001
Tributary sediment monitoring | bar: 2004
Survey channel bathymetry from LaGrange Dam to 7/11 haul road bridge to San Joaquin River
Monitor tributary fine sediment contribution | bar: CALFED PSP 2006 to CALFED PSP 2008
Benthic Macroinvertebrate monitoring | bar: CALFED PSP 2006 to CALFED PSP 2008
Quantify Chinook salmon spawning habitat selection and redd superimposition | bar: CALFED PSP 2006 to CALFED PSP 2008
TID/TRTAC, | Coarse Sediment Management 3, 4
CDFG | Publish Coarse Sediment Management Plan | bar: 2004
Document channel bed texture and monitor bed mobility thresholds | bar: 2001 to 2002; CALFED PSP 2006 to CALFED PSP 2008
Survey reach-scale channel cross sections and profile and quantify net sediment removal from augmentation sites: | bar: 2000 to 2001; CALFED PSP 2006 to CALFED PSP 2008
Sediment Transport Measurements at R4B | bar: 2003; 2005 to CALFED PSP 2008
Develop and test a predictive sediment transport model (Phase I) | bar: 2001
Develop and test a predictive sediment transport model (Phase II)
Map planform geomorphic and habitat features | bar: 1999 to 2001; CALFED PSP 2006 to CALFED PSP 2008
Monitor spawning substrate permeability: | bar: 1999; CALFED PSP 2006 to CALFED PSP 2008
Digital orthorectified aerial photos from LaGrange to San Joaquin River | bar: 2005
Floodplain LIDAR topography from LaGrange to San Joaquin River | bar: 2005
Survey channel bathymetry from LaGrange Dam to 7/11 haul road bridge | bar: 2005
Survey channel bathymetry from LaGrange Dam to 7/11 haul road bridge to San Joaquin River | bar: CALFED PSP 2006
1 Monitoring and funds indicated in these columns may not occur or be available in all years included in this CALFED-funded program. Red text indicates proposed modifications to PSP budget.
2 This predation study is funded by existing project monitoring funds and is not included in the CALFED PSP. The study was to be implemented in 2005 but was delayed until 2006 due to high flows in Spring 2005.
3 CDFG implemented coarse sediment augmentation projects at Riffle A7 (2001, 2003), Riffle 1A (2001, 2002), Riffle 1B (1994, 2002), Riffle 3A (1994), and Riffle 3B (1994). CDFG plans to add coarse sediment at Riffles 3A and 3B in 2006. FOT with TID/TRTAC completed Phase I of coarse sediment augmentation at Bobcat Flat in 2005. Additional projects included in Phase III of the Coarse Sediment Management Plan are expected to be implemented in 2006, pending approval of the CALFED contract amendment for the project (Tuolumne River Sediment Transfusion).
4 If approved by CALFED, the Tuolumne River Sediment Transfusion Project includes $400,000 for monitoring. Approximately $112,000 of that amount has been expended to date for surveys and aerial photography.
5 Included in Coarse Sediment Management project monitoring below.