## Monitoring status and funding
TUOLUMNE RIVER MONITORING SUMMARY (DRAFT)
Prepared for TRTAC October 13, 2005
Legend to codes in table:
date: | year study implemented or reported |  |  | Monitoring implemented and funded from sources other than Monitoring PSP
NI: | included in monitoring plan but not implemented
IP: | implementation pending |  |  | Initial monitoring implemented from sources other than Monitoring PSP. PSP funds required to continue monitoring.
RC: | report complete
RP: | report pending |  |  | Area where funding may become available due to delays in implementation or funding from other sources
F: | funded from source other than Monitoring PSP
NF: | not funded from source other then Monitoring PSP
N/A: | not included in monitoring plan for project
MONITORING PSP TASK |  | 2004 CALFED PSP |  |  |  | PAST AND ONGOING MONITORING STATUS
|  | 2006 | 2007 | 2008 | 2006-2008
|  | TOTAL | TOTAL | TOTAL | TOTAL
TASK 1. | PROJECT MANAGEMENT | 18000 | 18000 | 18000 | 54000
TASK 2. | PUBLIC PARTICIPATION | 8900 | 9300 | 67500 | 85700
2a. | TRTAC participation | 8900 | 9268 | 9654.4 | 27822.4
2b. | Brochure development | 0 | 0 | 25177.25 | 25177.25
2c. | CALFED Science Conference + publications | 0 | 0 | 32627 | 32627
TASK 3. | CONTINUE 7/11, MJR, AND SRP9 PROJECT MONITORING | 138100 | 72300 | 140500 | 350900 | 7/11 |  | Ruddy |  | SRP 9 |  | SRP 10 |  | Bobcat Flat4
[6 empty] | Pre-project | Post-project | Pre-project | Post-project | Pre-project | Post-project | Pre-project | Post-project | Pre-project | Post-project
N/A | Digital Terrain Mapping |  |  |  |  | complete (date?), RP | NI | complete (date?) | NF | complete (date?) | NI | complete (date?) | NF | 2004 | 2005, IP
N/A | Aerial photography |  |  |  |  | 1998, RP | 2002, RP | 1998, RP | NF | 1998, RP | 2002 | 1998, RP | NF | 2004 | 2005, IP
N/A | Habitat mapping |  |  |  |  | 1998/99, RP | 2002, RP | 1998/99, RP | NF | 1998/99, RP | NI | 1998/99, RP | NF | 2004 | 2005, IP
N/A | Habitat modeling |  |  |  |  | N/A | N/A | N/A | NF | 2004, RP | 2004 | 2005, RP | NF | N/A | N/A
N/A | Bioengineering photomonitoring |  |  |  |  | N/A | NI | ?? | NF | N/A | N/A | N/A | NF | N/A | N/A
N/A | Stochastic water surface monitoring |  |  |  |  | N/A | 2005 | N/A | NF | N/A | 2003/5 | 2005 | NF | 2003 (?) | ?
N/A | Electrofishing at prject and control sites |  |  |  |  | N/A | N/A | N/A | N/A | 1998/99, RP | 2003, RP | 1998/99, RP | NF | N/A | N/A
N/A | Juvenile salmon survival |  |  |  |  | N/A | N/A | N/A | N/A | 1998/99, RP | N/A | 1998/99, RP | N/A | N/A | N/A
N/A | Predation study |  |  |  |  | N/A | N/A | N/A | N/A | N/A | F, deferred 2005 | N/A | F, deferred 2005 | N/A | N/A
N/A | Pebble counts |  |  |  |  | 1998, RP | 2002, RP | 1998 (?) | NF | N/A | N/A | N/A | N/A | 2004 | 2005, IP
N/A | Bulk samples |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2005, IP
3a. | Resurvey cross sections and longitudinal profiles | 28551.95 | 9026.5 | 22188.5125 | 59766.9625 | 1998/99, RP | 2002, RP | 1999, RP |  | 1998/99, RP | 2002, RP | 1998/99, RP | NF |  | 2005, IP
3b. | Deploy and maintain tracer rocks | 8157.7 | 2579 | 6339.575 | 17076.275 |  | 2005 3 | [5 empty] | NF |  | 2005, IP
3c. | Map channel migration and other planform changes | 4078.85 | 1289.5 | 3169.7875 | 8538.1375 | [7 empty] | NF
3d. | Monitor peak flow water surface elevations (crest gages) | 11220 | 4367.1 | 3259.35 | 18846.45 | [7 empty] | NF
3e. | Continuous water surface monitoring (depth recorder) | 1800 | 0 | 0 | 1800 | [7 empty] | NF
3f. | Monitor planted vegetation | 21840 | 0 | 22890 | 44730 |  | as-built and Year 2 only, RP |  |  | as-built and Year 2 only, RP |  |  | NF
3g. | Monitor natural recruitment | 5470 | 6860 | 12910.4 | 25240.4 | [7 empty] | NF
3h. | Map spawning location and habitat characteristics | 20499.795 | 21012.2899 | 21537.5971 | 63049.682 | [7 empty] | NF | 2004 | 2005, IP
3i. | Conduct Siene Surveys | 0 | 0 | 0 | 0 | [7 empty] | NF
3j. | Monitor Groundwater | 13253.5 | 3545.6 | 3977.775 | 20776.875 | [7 empty] | NF
3k. | Monitor avian species | 15000 | 15000 | 15000 | 45000 | [7 empty] | NF
3l. | Report preparation and distribution | 8201 | 8604 | 29296 | 46101 | [7 empty] | NF
TASK 4. | CONTINUE FINE SEDIMENT MANAGEMENT MONITORING | 51700 | 89400 | 199200 | 340300 | Fine Sediment Management
[6 empty] | Pre-project |  |  |  |  | Post-project
N/A | Gasburg Creek Sediment Source Assessment |  |  |  |  | 2004, RC |  |  |  |  | as-built and Year 1: F, IP (2006, 2007)
N/A | Survival-to-Emergence Study |  |  |  |  | 2002, RP |  |  |  |  | as-built and Year 1: F, IP (2006, 2007)
N/A | Riffle cleaning pilot study |  |  |  |  | F, IP
N/A | Pool cleaning literature review |  |  |  |  | 2002, RC
N/A | Tributary sediment reconnaissance study |  |  |  |  | 2001, RC
N/A | Tributary sediment monitoring |  |  |  |  | 2004, RP
4a. | Quantify annual sediment accumulation | 0 | 13106 | 12537.25 | 25643.25
4b. | Monitor channel stability and riparian vegetation | 0 | 11393 | 19455.25 | 30848.25
4c. | Monitor tributary fine sediment contribution | 8407 | 8712 | 15414.5 | 32533.5
4d. | Benthic Macroinvertebrate monitoring | 14066.2732 | 23570.1861 | 76341.1294 | 113977.5887
4e. | Quantify Chinook salmon spawning habitat selection and redd superimposition | 29223.1578 | 32674.6349 | 63984.1218 | 125881.9145
4f. | Report preparation and distribution | 0 | 0 | 11475 | 11475
TASK 5. | AUGMENT BASELINE AND POST-PROJECT MONITORING FOR COARSE SEDIMENT AUGMENTATION | 169500 | 106300 | 139000 | 414800 | Coarse Sediment Management Plan |  | CDFG/CDWR Coarse Sediment Projects |  |  |  | Coarse Sediment Transfusion Phase III1
[8 empty] | Pre-project |  | Post-project |  | Pre-project |  | Post-project
N/A | Develop Coarse Sediment Management Plan |  |  |  |  | 2004, RC
N/A | Develop monitoring plan | [10 empty] | Draft RP
5a. | Document channel bed texture and monitor bed mobility thresholds | 19221 | 20182 | 21191 | 60594 | pebble counts |  | pebble counts |  | pebble counts, marked rocks |  | 2005 marked rocks
5b. | Survey reach-scale channel cross sections and profile and quantify net sediment removal from augmentation sites: | 31945 | 0 | 33542.25 | 65487.25
5c. | Sediment Transport Measurements at R4B | 33938 | 35634.9 | 37416.645 | 106989.545 | [6 empty] | 2005
| Develop and test a predictive sediment transport model2 | [10 empty] | $50,000 NF
5d. | Map planform geomorphic and habitat features | 24830 | 0 | 0 | 24830
5e. | Monitor spawning substrate permeability: | 27588.1491 | 16966.7117 | 11593.9197 | 56148.7805
5f. | Report Preparation | 31932 | 33528.6 | 35205.03 | 100665.63
TASK 6. | MONITORING OF CUMULATIVE EFFECTS ON TARGET POPULATIONS [CHINOOK SALMON AND O. MYKISS] | 269300 | 280400 | 335400 | 885100 | River-wide Monitoring
N/A | Water temperature |  |  |  |  | 1996-2005, RC (annual reports)
N/A | Water quality |  |  |  |  | 2004
N/A | Juvenile salmon survival (CWT releases) |  |  |  |  | 1996-2002, RC (annual reports)
N/A | Fish stranding |  |  |  |  | 1996, 1997, 1999, 2000, 2002
N/A | Riffle permeability |  |  |  |  | 2002, RC
6A. | Juvenile Chinook salmon production and outmigration timing | 131747.5 | 131747.5 | 131747.5 | 395242.5 | 1996-2005, RC (annual reports)
6b. | Juvenile Chinook salmon and O. mykiss distribution, abundance, and size (winter and spring) | 37609.2559 | 41150.7614 | 69962.9977 | 148723.015 | 1996-2005 (seining surveys), RC (annual reports)
6c. | Juvenile Chinook salmon and O. mykiss distribution (summer) | 33095.4367 | 34419.2542 | 35796.0244 | 103310.7153 | 1996-2005 (snorkel surveys), RC (annual reports)
6d. | Chinook salmon adult escapement and spawning distribution | 18960.8333 | 18960.8333 | 18960.8333 | 56882.5 | 1996-2005, RC (annual reports)
6e. | O. mykiss adult distribution | 34000 | 34000 | 34000 | 102000 | 1996-2005 (snorkel surveys), RC (annual reports)
6f. | Benthic macroinvertebrate composition, abundance, and diversity indices. | 13903.5218 | 20091.4437 | 44911.1793 | 78906.1448 | 1996, 1997, 2000-2005, RC
TASK 7. | AERIAL PHOTOGRAPHY, ORTHORECTIFICATION, PHOTOGRAMMETRY, AND BATHYMETRY | 299600 | 0 | 0 | 299600 | Coarse Sediment Transfusion Phase III
[6 empty] | Pre-project |  |  |  |  | Post-project
7a. | Air photo flight from LaGrange to San Joaquin River | 105000 | 0 | 0 | 105000 | 2005 |  |  |  |  | NF
7b. | Install ground control points | 36750 | 0 | 0 | 36750 | 2005 |  |  |  |  | NF
7c. | Orthorectify aerial photographs | 26425 | 0 | 0 | 26425 | 2005 |  |  |  |  | NF
7d. | Photogrammetry/LIDAR topography | 26425 | 0 | 0 | 26425 | 2005 |  |  |  |  | NF
7e. | Survey channel bathymetry | 105000 | 0 | 0 | 105000 | 2005 |  |  |  |  | NF
| TOTALS | 955100 | 575700 | 899600 | 2430400
1 The Sediment Trnasfusion Proposed Contract Amendment is curretnly being peer reviewed through UC-Davis. A response is expected in mid-October 2005. The originalproposal included $60,000 for monitoring. The amended proposal includes $400,000 for monitoring.
Approximately $112,000 has been expended for bedload trnasport measurements (April 2005), marked rock placement and recovery (2005), and aerial photography and surveys for orthorectification. Channel bathymetry and LIDAR surveys were funded through augmentation design task.
2 This model is referenced in Task 5C of the Monitoring PSP as funded under the Coarse Sediment Transfusion Project. The model is not inculded in the proposed amendment and is not currently funded.
3 Included in Sediment Transfusion monitoring
4 See also funding for Coarse Sediment Transfusion